Y Bwrdd Rheoli
Management Board

MB (01-10) Paper 6 (Part 1)

Financial Management Report

Date: 	18 January 2010
Time:	14:00-16:00
Venue:	Conference Room 4B
Author name and contact number: Nicola Callow, ext. 8054

Financial Management Report:

Year to Date Period Ended 30 November 2009

This paper has been prepared for consideration by the Management Board and has been deemed suitable for publication on the Internet after 1/3/10

OVERVIEW OF FINANCIAL PERFORMANCE FOR THE PERIOD

- The net spend to the end of November was £28.185million with £0.060 million returned to the contingency.  There is a variance of 0.5% against a forecast of £28.352 million for November.

- The latest forecast from budget managers, adjusted for the additional financial pressures identified in Note 7 means we are now expecting the year end outturn to be £1.179million under spent.  This reflects a 2.4% under-spend against the 2009-10 £49.701million budget.  This is outside the tolerance levels we have set ourselves and needs to be satisfactorily resolved.

- Supporting detailed analysis is provided in the Annex.

KEY MESSAGE TO THE BOARD (Red risk)

- The Management Board needs to finalise its plans for the projected under spend.  The options available are:

- bringing forward expenditure from 2010-11 into 2009-10; or

- surrendering the under spend to the Welsh Government; or

- reporting an under spend against the Commission’s budget.

- We can of course do a mixture of the above.  The ideal position would be an under spend of £250,000, 0.5% of the budget.  The maximum under spend we can tolerate is 2% of the 2009-10 Budget (£994,000), and anything under £500,000 would be a good position to achieve.

- Option A above provides an effective solution for 2009-10 as well as creating flexibility in the 2010-11 budget to manage the UNO funding requirements.  The items that have been identified so far are listed below.  Further options might include undertaking work on our carbon reduction programme; making a final push to complete our business continuity arrangements; and doing some preparatory work in developing our “trusted information provider” role in advance of a referendum:

  - £274,000	IT Licence costs arising from the UNO project

  - £  80,000	Additional funding requirement for the

Members Casework Project (subject to Change Board Approval)

  - £200,000	Fourth floor refurbishment,  furniture for A

Block

  - £ 12,000		Assembly Bilingual Service Review

- Option B has a time limit on it as the Welsh Government can only utilise these funds if we confirm our decision to them in the next two weeks as it plans to lay a Supplementary Budget soon after.  We can use this opportunity to formally surrender a set amount of under spend to the Government.  We will also be using this Supplementary Budget process to ensure that our 2009-10 Budget correctly reflects our revised Resource and Capital spending plans (which have separate allocations within the Approved Budget).

RISK ASSESSMENT ON THE APPROVED BUDGET FOR THE YEAR (£49.701million)

- Key risk areas within the budget, rated using Green for on target, Amber for potential risk and Red as off target, are:

The level of flexibility within the Commission’s overall budget and in-built Contingency; Note 7 sets out the forecast under spend of £1.179million for 2009-10.

UNO project – UNO remains at amber rating reflecting the slow spend to date and the significant delay in completing Phase 1, as a result of difficulties in settling the contractual arrangements with Siemens.  Some activity has now started; the licence order has been placed for a January delivery.  The project expenditure forecast reflects the anticipated agreement of contractual arrangements (the PSM) before Christmas.  Significant expenditure is profiled in January and February which is still achievable provided the PSM is signed early January.  All known issues with the PSM have been satisfactorily resolved and the signed PSM is expected by 11 January 2010.

Close liaison between the project and finance teams has highlighted the possibility that several projects within the Assembly Business Directorate may be affected by delays in the UNO project.  Delays in agreeing contractual terms mean that £0.800million will be required to complete the project in 2010-11 which will bring additional pressure on the 2010-11 budget, so that it is possible that a Supplementary Budget will be needed in 2010-11, depending upon the success we have in bringing forward expenditure.  Whilst slippage of this sort is unlikely to be a significant issue with the Welsh Government, particularly if it is matched with a similar level of returned under spend in 2009-10, it does expose the Commission to reputational risk, which would be mitigated by making best use of the resources available to us this year and surrendering those we do not need for the rest of the public sector in Wales.

Increased capital expenditure activity will result in the need to include the capital and resource budgets adjustments in the supplementary budget planned by the Welsh Government for February 2010.

The Members’ Pension Scheme Actuary has been asked to provide an estimate of the pension provision as at 31 March 2010.  Based on past experience we anticipate being able to release part of the provision further increasing the under spend.  The extent of the funds that may be released will be known by the middle of January.

The Pierhead project – The status has changed from an Amber rating last month to Green.  Phase 2 of the project is almost complete, with the building anticipated to be available for testing during late January.  Any potential financial risks are now greatly reduced with the project expected to come in on time and on budget.

Other matters to note

- In recognising the need to manage project costs separately from Service Budgets, Note 1 now shows the current position for UNO and the Pierhead to allow the board to assess progress.  We welcome the Management Board’s views on this change as it is our intention to report all major projects in this way.

- The financial year end is rapidly approaching.  The Accounts team will be circulating its annual request for your service area contributions to preparing the annual accounts.  For example, we will be seeking your creditor, debtor and fixed asset information.

- As one financial year ends, another starts so the Budget team will also be in contact soon to issue the 2010/11 budget allocations in readiness for 1 April 2010.

- And finally, a reminder that the Budget Framework document approved by the Chief Executive on 30 December 2009 has been circulated for information.  The Finance Team will liaise with Service Heads in coming weeks to help develop a strong understanding of its implications.

ACTIONS RECOMMENDED TO THE BOARD

- It is recommended that Board members:

  - Finalise their plans for the projected under spend.  The most effective solution is to identify areas of expenditure that can be brought forward into 2009/10 from 2010/11;

  - Consider the budget performance variances for their respective service areas;

  - Raise any significant issues which may not have been picked up in the forecast outturn projections.  Examples include estimated cost increases, new spend proposals, or potential savings/underspends which have not previously been identified; and

  - Review the key risks flagged in the report and consider whether any additional actions should be taken.

Annex to the Finance Management Report for the period April 2009 to November 2009

Note 1 	presents performance by service area and projects;

Note 2 	provides variance explanations;

Note 3 	summarises spend by type of expense;

Note 4 	provides an overview of the Contingency showing approved virements;

Note 5 	lists the potential further calls on the Contingency;

Note 6 	lists funds released from service areas, including in-year efficiencies, savings and under spends;

Note 7 	provides details of the forecast year-end outturn

- Budget Performance for the period April – November 2009-10

| Service |  | Forecast to date (£’000) |  | Actuals to date (£’000) |  | Variance for the period (£’000) |  | Variance % |  | 2009-10 Forecast Outturn (£’000) |  | 2009-10 Revised Annual Budget (£’000) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Unit |  | 1,105 |  | 1,115 |  | -10 |  | -1 |  | 1,797 |  | 1,844 |
| Legal Services |  | 378 |  | 381 |  | -3 |  | 0 |  | 600 |  | 647 |
| Change Board |  | - |  | - |  | - |  | - |  | - |  | - |
|  |  | 1,483 |  | 1,496 |  | -13 |  | -1 |  | 2,397 |  | 2,491 |
| OPERATIONS DIRECTORATE |  |  |  |  |  |  |  |  |  |  |  |  |
| Human Resources |  | 977 |  | 949 |  | 28 |  | -3 |  | 1,754 |  | 1,776 |
| Estate & Facilities Management |  | 4,614 |  | 4,540 |  | 74 |  | 1 |  | 7,538 |  | 7,534 |
| Financial Services |  | 488 |  | 489 |  | -1 |  | -1 |  | 795 |  | 749 |
| ICT |  | 2,683 |  | 2,723 |  | -40 |  | -1 |  | 4,875 |  | 4,818 |
| UNO Project |  | 112 |  | 45 |  | 67 |  | 60 |  | 2,086 |  | 2,650 |
| External Communications |  | 1,401 |  | 1,418 |  | -17 |  | -1 |  | 2,233 |  | 2,424 |
| The Pierhead |  | 270 |  | 130 |  | 140 |  | 52 |  | 1,109 |  | 300 |
| Security |  | 1,452 |  | 1,435 |  | 17 |  | 1 |  | 2,304 |  | 2,291 |
| Procurement and Sustainability |  | 92 |  | 89 |  | 3 |  | 3 |  | 142 |  | 132 |
|  |  | 12,089 |  | 11,818 |  | 271 |  | 2 |  | 22,836 |  | 22,674 |
| ASSEMBLY BUSINESS DIRECTORATE |  |  |  |  |  |  |  |  |  |  |
| Members’ Research Service |  | 1,236 |  | 1,212 |  | 24 |  | -2 |  | 1,823 |  | 1,921 |
| Chamber & Legislation Services |  | 680 |  | 678 |  | 2 |  | 0 |  | 1,099 |  | 1,121 |
| Translation & Reporting Service |  | 1,153 |  | 1,155 |  | -2 |  | 0 |  | 1,768 |  | 1,993 |
| Committee Service |  | 675 |  | 671 |  | 4 |  | 1 |  | 1,106 |  | 1,295 |
| Co-ordination Unit |  | 59 |  | 60 |  | -1 |  | -1 |  | 88 |  | 95 |
|  |  | 3,803 |  | 3,776 |  | 27 |  | -2 |  | 5,884 |  | 6,425 |
| Commission Services Total |  | 17,375 |  | 17,090 |  | 285 |  | 2 |  | 31,117 |  | 31,590 |
| Members Pay and Allowances |  | 8,177 |  | 8,191 |  | -14 |  | 1 |  | 12,400 |  | 12,759 |
| Potential demands on Contingency |  |  |  |  |  | 149 |  | 652 |
| Total – Cash Items |  | 25,552 |  | 25,281 |  | 271 |  | 2 |  | 43,666 |  | 45,001 |
| Depreciation & Notion Interest |  | 2,800 |  | 2,904 |  | -104 |  | 4 |  | 4,356 |  | 4,200 |
| Members Pension Provision |  | - |  | - |  | - |  | - |  | 500 |  | 500 |
| Total |  | 28,352 |  | 28,185 |  | 167 |  | 1 |  | 48,522 |  | 49,701 |
| Forecast Under spend |  |  |  |  |  |  |  |  |  | 1,179 |  |  |
| Total Budget Available |  |  |  |  |  |  |  |  |  | 49,701 |  |  |

- Explanation of Variances outside 2% Tolerance for period to November 2009

|  | Service/Variance % / £’000 |  | Reason for Variance |  | Action Being Taken to Rectify |
| --- | --- | --- | --- | --- | --- |
|  | Human Resources: 3% under budget |  | Leadership programme: Cancellation of November workshop 2009. Personal training and development: Outstanding invoice for £8,000 for FHE training. |  | Workshop rescheduled for December 2009. Cost will be reflected in December spend. Invoice will be received and processed by January 2010. Revised forecast submitted. |
|  | Procurement and Sustainability: 3% under budget |  | Sustainability Improvements: New budget line, spend less than expected. |  | Forecast has been amended. Spend for December 2009 is on target. |
|  | UNO: 60% £67K under budget |  | Significant delays to Phase 1 project documentation |  | Provided contract is signed in early January, spend can proceed at an accelerated rate as currently forecast. |
|  | The Pierhead 7% £140k under budget |  | Timing differences between November and December |  | Delay in receipt of invoices. Quantity Surveyor must approve work before being paid, which leads to longer delays than originally anticipated. |

- Forecast  Vs Actuals to Date – Grouped by Expense Type

- Virements

| Contingency Balance: |  | Released from Service Budgets (£’000) |  | Allocated to Service Budgets (£’000) |  | Contingency Balance at End of Month (£’000) |
| --- | --- | --- | --- | --- | --- | --- |
| Opening working balance 01/04/09 |  |  |  |  |  | 983 |
| April |  | 793 |  | -461 |  | 1,315 |
| May |  | 210 |  | - |  | 1,525 |
| June |  | - |  | -60 |  | 1,465 |
| July |  | - |  | - |  | 1,465 |
| August |  | - |  | -166 |  | 1,299 |
| September |  | 276 |  | - |  | 1,575 |
| October |  | 40 |  | -73 |  | 1,542 |
| November |  | 60 |  | -950 |  | 652 |
| Current Balance |  | 1,379 |  | -1,710 |  | 652 |

| Summary of potential demands as at 30 November 2009 |
| --- |
| Service | Potential Demands | Estimated value (£’000) of potential demands at 31 October 2009 | Update as at 30 November 2009 | Change in Estimated values (£’000) | New Demands in November 2009 (£’000) | Allocated from Contingency to Service Budget in November 2009 (£’000) | Estimated Potential call at 30 November 2009 |
| ICT | Changes to FTR Gold | 10 | Yet to be allocated. Awaiting confirmation that existing budget can accommodate expenditure. |  |  |  | 10 |
| Corporate Unit | New Posts – change programme | 114 | Yet to be allocated. Awaiting formal project structure. |  |  |  | 114 |
| HR | New Assembly directory (DOB). | - | Yet to be allocated. Awaiting formal project structure. |  | 25 |  | 25 |
|  | TOTAL | 124 |  | 0 | 25 | 0 | 149 |

- Funds released from Service Budgets including In–Year Efficiencies, Savings and budget reductions

| Service |  | Details |  | Recurring (£'000) |  | Non -Recurring (£'000) |
| --- | --- | --- | --- | --- | --- | --- |
| Committee Service |  | Returned from Advisors – expenses/witnesses account, as not expected to be spent based on historical spend |  |  |  | 28 |
|  |  | Returned from staff costs line (no posts removed) |  |  |  | 50 |
| EFM |  | Returned from Agency staff budget line as not expected to be spent, based on historical spend |  |  |  | 40 |
|  |  | Returned from Window Cleaning – as cost is fixed and additional funds were not required. |  |  |  | 11 |
|  |  | Returned from Dry Cleaning, as dry cleaning costs are no longer incurred as a result of buying new uniforms |  |  |  | 3 |
|  |  | Returned from refuse budget, following an allocation error |  |  |  | 58 |
| Members’ HR |  | Returned based on historic spend and current spending expectations |  |  |  | 226 |
|  |  | Returned from AMSS T&S budget, as not expected to be spent, based on historical spend |  |  |  | 87 |
|  |  | Returned from AM database project |  |  |  | 8 |
|  |  | Members’ Contingency no longer required |  |  |  | 330 |
|  |  | Money returned from AM salary budget |  |  |  | 60 |
| External Communications |  | Release of funds from Marketing & Publicity to fund Pierhead |  |  |  | 300 |
| MRS |  | Money returned from ICT project as in-house solution found |  |  |  | 40 |
| Corporate Unit |  | Money returned from various budgets as not expected to be spent |  |  |  | 19 |
| ICT |  | Money returned from various budgets as not expected to be spent |  |  |  | 4 |
| HR |  | originally allocated for ICT project that is not expected to go ahead this year |  |  |  | 75 |
| Chamber |  | Money returned from ICT project budget line |  |  |  | 40 |
| Total |  |  |  |  |  | 1,379 |

- Projected Final Outturn (Over)/Under-spend

|  |  | £’000 |  | £’000 |
| --- | --- | --- | --- | --- |
| Original Contingency Budget |  |  |  | 1,000 |
| Less Required Efficiency Savings (in approved budget) |  |  |  | (250) |
| Add Savings identified prior to 1 April 2009 |  |  |  | 233 |
| Add Funds released from Service Budgets including In–Year Efficiencies, Savings and budget reductions |  |  |  | 1,379 |
| Less additional funds already allocated to service budgets |  |  |  | (1,710) |
| Current Balance (Note 4) |  |  |  | 652 |
| Add Expected under spend on members’ allowances |  | 359 |  |  |
| Projected Services overspend |  | 473 |  | 832 |
| Less Increase in depreciation & notional interest charges |  | (156) |  | (156) |
| Current Forecast Under-spend (before additional pressures) |  |  |  | 1,328 |
| Additional Financial Pressures: (Note 5) |  |  |  |  |
| Additional Staffing costs (various) |  | (114) |  |  |
| Other smaller amounts |  | (35) |  | (149) |
| Projected (overspend)/under-spend balance |  |  |  | 1,179 |

# Text boxes

R

A

A

A

G