Y Bwrdd Rheoli
Management Board

MB (06-09) Paper 6 (Part 1)

Financial Management Report – Year to Date

Date: 	20 July 2009
Time:	10:00-12:00
Venue:	Conference Room 4B
Author name and contact number: Chris Koehli, Interim Head of Finance

Financial Management Report:

Year to Date Period Ended 30 June 2009

This paper has been prepared for consideration by the Management Board and has been deemed suitable for publication on the Intranet site.

Purpose and summary of issues

The purpose of this report is to highlight, for the Management Board, the significant issues effecting the Assembly’s financial  performance and, in particular:

- To summarise the financial performance for the year-to-date period, ended 30 June 2009;

- To identify the risks and opportunities in managing the Assembly’s financial resources for the remainder of the year;

- To recommend actions to the Management Board on maximising the resources available.

Day to day management of less significant matters will continue to be undertaken by budget holders supported by the Financial Control Team.

The key messages are:

- The current spend to date is £8.840million.  This represents an underspend of £0.753million or 8% against the profiled budget of £9,634m. Most of this underspend is accounted for by timing differences and the true underspend is £0.222 million (2%);

- Current potential calls on the Contingency Balance amount to approximately £1.968million.  This figure includes £0.717million of the total of £2.7million required for the Unified Network project.  Consequently the supplementary budget for the Unified Network will cover the balance of £1.95million.

- The total potential calls on the Contingency could result in a potential overspend of £0.503million, but further potential savings have been identified to balance the position;

- The preliminary projection for the year is a small overspend of £13k.  In view of this being the first quarter review, this level of overspend will be managed down as the year progresses.

Recommendations

That the Board:

- reviews the financial performance for the year to date;

- notes the risks and takes action to mitigate them as far as is possible; and

- supports the action to deliver the additional savings necessary to deliver final outturn within budget.

Discussion

Financial performance in the first quarter indicates an underspend of £0.222 million (2%).  Analysis of the spend to date also suggests a need for a thorough review of the existing profiles and the Finance Team will be working with Budget holders over the next couple of weeks to achieve a more accurate profile of expenditure for the remainder of the year.

Current projections indicate the need to identify further savings of over £0.500 million in order to achieve a final outturn within budget.  Areas to achieve these savings have been identified but further action to identify further savings and efficiencies will be progressed by the Finance Team in liaison with Service Heads.

Risks - Red Flag Issues

( Overall budgetary performance for the period ended June 2009 is outside the 2% tolerance, further information on individual service performance can be found in note 1 of the annex.

( Contingency funding is currently potentially overspent but the Finance Team has identified savings that, if delivered, will bring the position back in to balance.

( The ability to meet funding requests outlined in notes 6 and 8 is, to a large extent, dependent on the eventual cost and completion of the Pierhead project.  The current estimate of £1.050million, includes all current known costs but the delay in the issue of listed building consent could impact significantly on both the cost and completion of the project.  The net impact on the total budget is currently estimated at £0.750million, with the balance being funded by savings from within the External Communications budget.

( None of the £0.373million in-year savings and efficiencies identified so far is recurring. Information on in year efficiency savings can be found at note 7.

3.4	Opportunities -Green Flag Issues

( Significant savings have already been identified and transferred to contingency.  (See note 5 of Annex).  An update on potential calls on contingency can be found in note 6 of the annex with details of further potential in year savings in note 8.

- Budget Performance for the period April – June 2009-10

| Service |  | Profiled budget (£’000) |  | Actuals to date (£’000) |  | Budget remaining for the period (£’000) |  | Variance % |  | 2009-10 Annual Budget (£’000) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Unit |  | 365 |  | 332 |  | 33 |  | 9 |  | 1,787 |
| Legal Services |  | 162 |  | 121 |  | 41 |  | 25 |  | 647 |
|  |  | 527 |  | 453 |  | 74 |  | 14 |  | 2,434 |
| OPERATIONS DIRECTORATE |  |  |  |  |  |  |  |  |  |  |
| Human Resources |  | 384 |  | 411 |  | -27 |  | -7 |  | 1,426 |
| Estate & Facilities Management |  | 1,745 |  | 1,830 |  | -85 |  | -5 |  | 7,660 |
| Financial Services |  | 188 |  | 182 |  | 6 |  | 3 |  | 723 |
| Members Pay & Allowances |  | 3,283 |  | 3,065 |  | 218 |  | 7 |  | 13,045 |
| ICT |  | 897 |  | 527 |  | 370 |  | 41 |  | 4,778 |
| External Communications |  | 551 |  | 495 |  | 56 |  | 10 |  | 2,724 |
| Security |  | 570 |  | 449 |  | 121 |  | 21 |  | 2,281 |
|  |  | 7,618 |  | 6,959 |  | 659 |  | 9 |  | 32,637 |
| ASSEMBLY BUSINESS DIRECTORATE |  |  |  |  |  |  |  |  |  |  |
| Members’ Research Service |  | 472 |  | 479 |  | -7 |  | -1 |  | 1,922 |
| Chamber & Legislation Services |  | 263 |  | 249 |  | 14 |  | 5 |  | 1,161 |
| PTRS |  | 422 |  | 413 |  | 9 |  | 2 |  | 1,993 |
| Committee Service |  | 308 |  | 265 |  | 43 |  | 14 |  | 1,345 |
| Co-ordination Unit |  | 23 |  | 22 |  | 1 |  | 2 |  | 95 |
|  |  | 1,488 |  | 1,428 |  | 60 |  | 4 |  | 6,516 |
| Depreciation & Notional Interest |  | 1050 |  | 1090 |  | -40 |  | -4 |  | 4,200 |
| Members Pension Fund Provision |  |  |  |  |  |  |  |  |  | 500 |
| Contingency |  |  |  |  |  |  |  |  |  | 1,134 |
| Members Contingency |  |  |  |  |  |  |  |  |  | 330 |
| Totals |  | 10,683 |  | 9,930 |  | 753 |  | 7 |  | 47,751 |

- Explanation of Variances outside 2% Tolerance for period to June 2009

| Service |  | Variance (£’000) |  | Reason for Variance |  | Action Being Taken to Rectify |
| --- | --- | --- | --- | --- | --- | --- |
| Corporate Unit |  | 9% under budget 34 |  | Overspend on staff costs (14). Invoices for External Audit costs accrued in 2008-09 (39) not yet received. |  | Staff costs are being examined by Finance. External Audit costs should fall into line once invoices for work carried out last year are received. |
| Legal Services |  | 25% Under budget 40 |  | Due to underspends on staff costs, caused by vacancies (22), legal costs (6) and Information services |  | Staff costs will be reprofiled, but full budget will remain as it is needed to cover a new SEO from September. Legal costs are demand led, so it has been agreed that all the spend will be profiled in month 12 and adjusted as and when expenditure incurred. An invoice for the 1st quarter for Information Services is expected imminently. |
| Human Resources |  | 7% over budget 27 |  | Insurance costs over spent (60), but balanced by underspends totalling 33k |  | No extra funding is required currently, but budgets will be reprofiled to reflect the pattern of spending. |
| EFM |  | 5% over budget 85 |  | Delay in receiving invoices (214). Delay in settling invoices accrued in 2008-09 (203). Office rentals (519) overspend, due to the fact that 2nd quarter has been paid but not reflected in the profile |  | The invoices have now been processed and profiling should fall into line in July. A dispute with Integral regarding a large bill for works and projects has been resolved and profile should into line in July. The profile will be amended to reflect any major changes. |
| Members’ Pay and Allowances |  | 7% under budget 218 |  | Mainly due to Members not claiming full entitlements (170) and underspends on AMSS salary related costs |  | Finance have identified this as a potential saving to be returned to Contingency |
| ICT |  | 41% under budget 370 |  | The major cause is invoices not being received when expected (229). |  | These invoices will be processed during July and the profile will be amended to reflect this |
| Committee Service |  | 14% Under budget 43 |  | Underspend on staff costs (14) caused by vacancies. Underspend on AM and staff travel as anticipated visits have been postponed (27). |  | A service restructure is currently underway, and the underspend will soon be eliminated. AM and Staff travel budgets have been reduced to reflect historical spend and will be returned to contingency and budget lines reprofiled. |
| External Communications |  | 10% Under Budget 56 |  | Due to a delay in receiving invoices (31), a delay in the Pierhead project while awaiting listed building consent (16), and staffing vacancies (7). |  | Budgets will be reprofiled and vacancies are being filled. |
| Security |  | 21% under budget 121 |  | Mainly due to a delay receiving police invoices (153) |  | There is no longer a delay with the invoices and each monthly period will be paid the following month as profiled. |

- Profiled Budget Vs Actuals to Date – Grouped by Expense Type

- Virements

| Contingency Balance: |  | Released from Service Budgets (£’000) |  | Allocated to Service Budgets (£’000) |  | Contingency Balance at End of Month (£’000) |
| --- | --- | --- | --- | --- | --- | --- |
| Opening working balance 01/04/09 |  |  |  |  |  | 983 |
| April |  | 163 |  | -161 |  | 985 |
| May |  | 210 |  | - |  | 1,195 |
| June |  | - |  | -60 |  | 1,135 |
| Sub Total |  | 373 |  | -221 |  | 1,135 |
| Potential Calls |  |  |  |  |  | -1,968 |
| Members Contingency |  |  |  |  |  | 330 |
| Potential Remaining Balance (sub total) |  |  |  |  |  | -503 |

| Service | Potential Demands | Estimated value (£’000) of potential demands at 31 May 2009 | Situation as at 30 June 2009 | Estimated value (£’000) of additional bids in June 2009 | Released to Contingency in June 2009 (£’000) | Allocated from Contingency to Service Budget in June 2009 (£’000) | Estimated Potential call at 30 June 2009 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| External Communications | Phase 2 (&3?) of Pierhead Project | 750 | Precise costs not known - estimate based on original total budget of £1.1 million less anticipated spend in 2008-09. Subject to change |  |  |  | 750 |
|  | Hospitality for Commissioners | 3 | Yet to be allocated. Removed from Corporate Unit Budget – may not be needed |  |  |  | 3 |
| ICT | Unified Network | - | New Bid in June – yet to be allocated | 717 |  |  | 717 |
|  | Changes to FTR Gold | 10 | Yet to be allocated |  |  |  | 10 |
|  | Installation of technical equipment | 34 | Yet to be allocated |  |  |  | 34 |
| Corporate Unit | New Posts (1x G6 and 1x SEO) to support Unified Network | - | New Bid in June – yet to be allocated . | 114 |  |  | 114 |
|  | Further External Audit work | 5 | Yet to be allocated |  |  |  | 5 |
|  | Extension of Members Review panel until Jan 10 - extra funds required | TBC | Yet to be allocated. Awaiting business case |  |  |  | TBC |
| EFM | Further costs for refurb 3A | 87 | Yet to be allocated. Awaiting business case |  |  |  | 87 |
|  | ROP Screens/Booths | 25 | Yet to be allocated. Awaiting business case |  |  |  | 25 |
|  | Green Team | 16 | Yet to be allocated. Removed from Corporate Unit Budget – may not be needed |  |  |  | 16 |
|  | Car Parking additional funds | 60 | Yet to be allocated. Awaiting business case |  |  |  | 60 |
| HR | Leadership Programme | 100 | To be allocated when programme reviewed |  |  |  | 100 |
|  | Insurance | 5 | Yet to be allocated |  |  |  | 5 |
| MRS | Amendments to salary | 6 | Yet to be allocated |  |  |  | 6 |
| Finance | Part time HEO post | 36 | Yet to be allocated |  |  |  | 36 |
|  | TOTAL | 1,137 |  | 831 |  |  | 1,968 |

- In – Year Efficiencies and  Savings

| Service |  | Details |  | Recurring Efficiencies (£'000) |  | Non -Recurring Efficiencies (£'000) |
| --- | --- | --- | --- | --- | --- | --- |
| Committee Service |  | Returned from Advisors – expenses/witnesses account, as not expected to be spent based on historical spend |  |  |  | 28 |
| EFM |  | Returned from Agency staff budget line as not expected to be spent, based on historical spend |  |  |  | 40 |
|  |  | Returned from Window Cleaning – as cost is fixed and additional funds were not required. |  |  |  | 11 |
|  |  | Returned from Dry Cleaning, as dry cleaning costs are no longer incurred as a result of buying new uniforms |  |  |  | 3 |
|  |  | Returned from refuse budget, following an allocation error |  |  |  | 58 |
| Members’ HR |  | Returned from AMSS T&S budget, as not expected to be spent, based on historical spend |  |  |  | 87 |
|  |  | Returned from AM database project |  |  |  | 8 |
| MRS |  | Money returned from ICT project as in-house solution found |  |  |  | 40 |
| Corporate Unit |  | Money returned from various budgets as not expected to be spent |  |  |  | 19 |
| ICT |  | Money returned from various budgets as not expected to be spent |  |  |  | 4 |
| HR |  | originally allocated for ICT project that is not expected to go ahead this year |  |  |  | 75 |
| Total |  |  |  | - |  | 373 |

8. Projected Final Outturn Over/Underspend

|  |  | £’000 |  | £’000 |
| --- | --- | --- | --- | --- |
| Original Budget |  |  |  | 1,000 |
| Less Efficiency Savings |  |  |  | (250) |
| Add Savings identified prior to 1 April 2009 |  |  |  | 233 |
|  |  |  |  | 983 |
| Savings already realised |  |  |  | 373 |
| Members Contingency released |  |  |  | 330 |
| Vacancy factor |  |  |  | 150 |
| Expected underspend on members allowances |  |  |  | 500 |
|  |  |  |  | 2,336 |
| Additional Financial Pressures: |  |  |  |  |
| Funds already allocated to service budgets |  | (221) |  |  |
| Additional Staffing costs |  | (156) |  |  |
| Pierhead (net of £0.300m savings in External Comms budget) |  | (750) |  |  |
| LDP |  | (100) |  |  |
| 3A further costs |  | (87) |  |  |
| Car parking |  | (60) |  |  |
| Depreciation & notional interest |  | (160) |  |  |
| Other smaller amounts |  | (98) |  | (1472) |
| Sub total |  |  |  | 704 |
| Unified network |  |  |  | (717) |
| Projected overspend/ Unallocated balance |  |  |  | (13) |